## Sheet1
Sprint 1 Retrospective – HealthPulse: Real-Time AI-Based Health Trend Monitoring System
What went well | What went poorly | What ideas do you have | How should we take action
Positive outcomes and successes from Sprint 1 of HealthPulse. | Challenges, blockers, or issues encountered during Sprint 1 development and testing. | Suggestions and ideas for improving processes, tools, and collaboration in Sprint 2. | Specific action items and steps assigned to team members for Sprint 2 execution. | Guidelines
Sprint 1 ML Goal Achieved: SARIMAX models trained for all 48 region-keyword pairs. XGBoost classifier achieved ~98% accuracy on initial test data. | SARIMAX model encountered a Prophet optimization error (line-search failure) during initial runs, requiring significant debugging time. | Introduce a fallback model strategy from the start — Gradient Boosting Regressor is now ready as SARIMAX backup. | Data Scientist (AJ) to document all model fallback scenarios and add automated switching logic before Sprint 2 training begins. | Story 1
All functional test cases executed with 100% pass rate. Data ingestion, preprocessing, and both ML models (SARIMAX + XGBoost) worked correctly on initial datasets. | Debugging the MongoDB SSL/URI connection issue took longer than estimated, delaying data storage testing by approximately 2 days. | Create a standardized environment setup checklist and pre-test all external connections (MongoDB, Google Trends API) before Sprint 2 begins. | Backend (KT) to prepare a shared environment config document and run connection health checks before any Sprint 2 development session. | Testing
Clear task distribution: Aditya focused on Data & ML (model design, preprocessing, XGBoost), Kshitij on Backend & Integration (MongoDB, APIs, environment). Daily progress sharing kept both aligned. | Asynchronous work led to some environment configuration gaps — one member's virtual environment had missing dependencies discovered late. | Use a shared requirements.txt and Docker container to standardize the development environment across all team members. | Both members to validate their environments against a master requirements.txt; KT to set up a shared Docker environment for Sprint 2. | Teamwork
Sprint 1 data pipeline delivered on schedule. SARIMAX avg RMSE ~9–11 across regions is within acceptable range for initial testing. XGBoost confidence consistently above 0.99. | Fever keyword consistently showed highest RMSE (13.60–13.98) across all regions, indicating noisy or non-seasonal search behaviour for this term. | Add dedicated feature engineering for high-RMSE keywords like Fever — explore additional exogenous variables such as weather correlation. | AJ to research additional features for Fever modeling; QA to add Fever-specific edge case scenarios to Sprint 2 test cases. | Quality
Code was structured modularly (backend/, app/ directories). Git version control was used for all code files. | No formal Git branching strategy was followed, leading to merge conflicts on shared pipeline scripts. | Adopt a Git branching strategy (e.g., feature branches: feature/sarimax-model, feature/mongo-pipeline) so each module is developed independently. | Both members to set up Git repository with branch naming conventions and pull request reviews before Sprint 2 development begins. | Process